🗺️ Implementation Roadmap

IoT Smart Crop Prediction System — AgriSense AI

6-Phase Plan  |  Estimated Duration: 20–26 Weeks

| Phase 1 2–3 Wks | Phase 2 3–4 Wks | Phase 3 3–4 Wks | Phase 4 4–5 Wks | Phase 5 4–5 Wks | Phase 6 4–5 Wks |
| --- | --- | --- | --- | --- | --- |
| Foundation & APIs | IoT Layer & MQTT | ML Engine & Fusion | Geospatial & Twin | Dashboard & UI | Optimize & Deploy |

PHASE 1 — Foundation & API Integration  (Weeks 1–3)

Goal: Build the project skeleton, connect all external data APIs, and establish the backend data pipeline.

Week 1 — Project Setup

- Initialise monorepo: FastAPI backend + React frontend + Docker Compose

- Set up PostgreSQL schema: fields, zones, sensor_readings, predictions tables

- Configure Firebase Realtime Database for live dashboard sync

- Create project config system (env vars, API keys manager, logging)

Week 2 — API Integration

- Integrate OpenWeatherMap and Open-Meteo (current + 16-day forecast)

- Integrate NASA POWER API for solar radiation data

- Integrate SoilGrids ISRIC REST API for soil profiles

- Integrate USGS Elevation API for terrain data

Week 3 — Data Fusion Layer

- Implement Kalman filter and weighted API fusion algorithm

- Build data normalisation and unit conversion pipeline

- Write unit tests for fusion accuracy using historical data

- Deliverable: API returns fused virtual sensor readings for any GPS coordinate

PHASE 2 — IoT Architecture & MQTT Layer  (Weeks 4–7)

Goal: Simulate the full IoT hardware stack including MQTT protocol, edge computing node, and stream processing.

Week 4 — MQTT Broker & Sensor Simulation

- Connect HiveMQ Cloud MQTT broker to backend

- Build sensor simulator: publishes fused API readings to MQTT topics (field/zone/sensor)

- Backend subscribes, ingests, stores in PostgreSQL time-series table

Week 5 — Edge Node Simulation

- Build edge processing module: local normalisation, outlier filtering, compression

- Implement fault injection: randomly disable sensors, trigger fallback logic

- Edge output feeds into cloud pipeline — two-stage data flow established

Weeks 6–7 — Stream Processing Pipeline

- Implement Kafka-style pipeline in Node.js: ingest → validate → transform → feature engineer

- Schema validation with rejection queue for malformed readings

- Feature engineering: compute derived metrics (ET0, soil moisture deficit, heat accumulation)

- Deliverable: Live pipeline running with MQTT data flowing end-to-end to feature store

PHASE 3 — ML Engine & Prediction Core  (Weeks 8–11)

Goal: Build, train, and wire up the ensemble ML prediction models with time-series forecasting.

Weeks 8–9 — Ensemble Model Training

- Collect and clean public crop dataset (Kaggle Crop Recommendation dataset)

- Train Random Forest model with soil + weather features

- Train SVM (RBF Kernel) classifier for binary crop suitability

- Train LSTM on 30-day historical weather sequences (PyTorch or Keras)

- Implement weighted voting ensemble layer with configurable weights

Week 10 — Forecasting Pipeline

- Integrate Prophet for 14-day forecast generation from historical API data

- Feed forecast features into LSTM — predict crop on future conditions

- Generate forecast confidence bands (upper/lower bounds)

Week 11 — Anomaly Detection & RL Feedback

- Implement Z-score and IQR-based anomaly detection on sensor streams

- Build alert tiering system: Info / Warning / Critical with action recommendations

- Stub out RL feedback loop with Q-learning reward shaping (simulated yield outcomes)

- Deliverable: POST /predict returns ensemble recommendation with confidence + forecast

PHASE 4 — Digital Twin & Geospatial Layer  (Weeks 12–15)

Goal: Build the digital twin, interactive field map, soil profile model, and geospatial intelligence features.

- Integrate Mapbox/Leaflet.js — field draw tool with polygon zone splitting

- DEM elevation data fetch → compute slope, aspect, drainage risk per zone

- Build digital twin grid model: N×M cell spatial state management

- Fetch and render NDVI overlay from NASA Earthdata or Sentinel Hub

- 3D soil profile model: topsoil / subsoil / bedrock layer data per zone

- Microclimate simulation: interpolate temperature and moisture across cells

- Deliverable: Interactive field map with per-zone crop recommendations rendered live

PHASE 5 — Frontend Dashboard & UI Build  (Weeks 16–20)

Goal: Build the full React frontend with all animated UI components, circuit canvas, and interactive panels.

Weeks 16–17 — Circuit Animator & Sensor UI

- SVG circuit board component: sensors → microcontroller → edge node → cloud

- Animated data pulse particles flowing along wire paths

- Live oscilloscope waveform per sensor channel using D3.js

- Fault simulation UI: click sensor to inject fault, watch fallback activate

Weeks 18–19 — Prediction & Analytics Panels

- Ensemble voting panel: model debate cards with confidence meters

- 14-day forecast chart with confidence bands (Recharts)

- Workflow DAG visualiser with animated edges (React Flow)

- Per-zone confidence heatmap overlay on field map

Week 20 — Planning Tools

- Crop rotation planner: 4-season calendar with market price tags

- Irrigation scheduler: daily water budget output table per zone

- Anomaly alert feed: real-time scrollable list with severity badges

- Deliverable: Full dashboard functional end-to-end in browser

PHASE 6 — Optimisation & Deployment  (Weeks 21–26)

Goal: Performance tuning, RL feedback integration, comprehensive testing, Docker deployment, and documentation.

- Finalise Q-learning RL feedback loop — tune reward function with simulated outcomes

- Performance profiling: API response times, ML inference latency, frontend frame rate

- PostgreSQL query optimisation: indexes on time-series tables, caching layer

- Docker Compose production setup: Nginx, FastAPI, PostgreSQL, MQTT bridge

- CI/CD pipeline (GitHub Actions): lint, test, build, deploy

- End-to-end integration tests covering full data pipeline

- Write comprehensive README, API documentation (FastAPI /docs), and architecture diagram

- Record demo video walkthrough of all major features

Timeline & Milestone Summary

| Phase | Duration | Key Milestone | Difficulty |
| --- | --- | --- | --- |
| 1 | Weeks 1–3 | Fused virtual sensor API live for any GPS coordinate | ⭐⭐⭐ |
| 2 | Weeks 4–7 | MQTT pipeline end-to-end with edge simulation running | ⭐⭐⭐⭐ |
| 3 | Weeks 8–11 | Ensemble ML predictions with forecast and anomaly detection | ⭐⭐⭐⭐⭐ |
| 4 | Weeks 12–15 | Interactive digital twin field map with per-zone predictions | ⭐⭐⭐⭐ |
| 5 | Weeks 16–20 | Full React dashboard with circuit animator and all panels | ⭐⭐⭐⭐ |
| 6 | Weeks 21–26 | Deployed, documented, RL integrated, production-ready | ⭐⭐⭐⭐⭐ |

Total Estimated Duration: 20–26 weeks  |  Complexity Level: Expert  |  Stack: Full-Stack IoT + ML + Geospatial